## backlog
Backlog Table
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | Truck Driver | see the order | so he can know how much material and which material to pick up and from which supplier or from which warehouse |  |  |  |  | shirel used for requierments
2 | Truck Driver | Edit the order | to update the quantity he picked up from the supplier/ warehouse and if the full amount was received/ exists in the stock |  |  |  | ** here the system will update (add) to current supply when received
3 | administrative staff | create an order | so a new order will be accepted in the system and could be worked on
4 | administrative staff | add first quality check to the new order | So the right material will be used and to make sure the order can be produced in the following day
5 | administrative staff | Record current/available stock numbers | The production line knows what materials are available to work with
6 | Production worker | see the order | can know what is being made
7 | Production worker | look at the pallet schematic (from erp) | know what design needs to be set up on the machine
8 | Production worker | Edit the order | note any issue with production or missing supplies
9 | Production worker | Complete the order | the compay knows when it is ready to be transported
10 | Production worker | Note when the production line stops | can record any machine problems/delays while producing the order
11 | Mangement | see the list of orders | know the status of each order
12 | Management | see the production time of each order | know how long each type of order takes
13 | Management | See details of production times and order delays (graphs/charts) | better plan future orders, know of reoccurring machine issues during an order
14 | Quality Control worker | record hourly quality checks | they know how many pallets meet their quality standards
15 | Quality Control worker | update the order details | have the correct quantity of sellable stock created
16 | Quality Control worker | update the order details | check and update the available, usable materials

## Backlog Updated
Requierments in Report |  | Backlog Table
Name of group member | Exists in Report | ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
Shirel | Yes | 1 | Production Related Worker | Choose the view I want according to my role | I can see and have access to the relevant features to my role | medium
| Yes | 2 | Production Related Worker | Choose the production machine I am working on | I can see and have access to the relevant features to my role and line I am working on | high
| Yes | 3 | Production Related Worker | See the General Reports | I can keep track of the logs of all production machines and their statistics | high
| Yes | 4 | Production Related Worker | See the reports per machine | I can keep track of the logs of that production machine and its statistics | high
| Yes | 5 | Production Related Worker (not truck driver) | See the notes and errors per production line with time and on which order they were logged | They can keep track on problems and comments on production | high
Deji | Yes | 6 | Truck Driver | See the orders scheduled for today and tomorrow | I have an organized list of tasks to do and organize my work day | high
| Yes | 7 | Truck Driver | See the details of materials for a specific order | I can pick up the correct material from the warehouse | high
| Yes | 8 | Truck Driver | See the location and quantity of the pallets existing in storage | I can deliver the produced pallets to the correct location | high
| Yes | 9 | Truck Driver | See current task for each order | I know what I need to do (deliver/ pick up) and where to | medium
| Yes | 10 | Truck Driver | Add new location of pallets if the old ones are full | The administration can know where they are stored | high
| Yes | 11 | Truck Driver | Update status of each task for each order | The other workers can see where the order is standing | low
| Yes | 12 | Truck Driver | Add notes for the other truck drivers for each order | Other truck drivers can be updated of changes | medium
| Yes | 13 | Truck Driver | View the hourly check ups for the production Machine I am working on | I can see if there were problems reported | low
| Yes | 14 | Truck Driver | Add a new log to the hourly check up for the production machine I am working on | I can report if I notice a problem with the pellets produced | low
Shirel | Yes | 15 | Administration Team | Create a new order in the system | a new order will be accepted in the system and could be worked on | high
| Yes | 16 | Administration Team | Create a new initial checklist for an order | the right material will be used and to make sure the order can be produced in the following day | high
| Yes | 17 | Administration Team | See all the orders, ordered by priority | I can have an overview of the orders' statuses | medium
| Yes | 18 | Administration Team | Update the initial check list of an order | the order will have an updated checklist in case of changes in conditions | medium
| Yes | 19 | Administration Team | See the initial checklist of each order | I can view that everything was filled in correctly and according to the latest status | high
| Yes | 20 | Administration Team | See the details of each order | I can view that everything was filled in correctly and according to the costumer's desires | high
| Yes | 21 | Administration Team | Update the order`s details | the order files will be updated according to changes or additional requierments from the costumer | medium
| Yes | 22 | Administration Team | View drawings of pallets in order | I can see which drawings are sent for the production team. | low
| Yes | 23 | Administration Team | View drawings' details of pallets in order | I can see which drawings details are sent for the production team. | low
Nick | Yes | 24 | Head Operator | View the main page | I can see the list of orders for the day | medium
| Yes | 25 | Head Operator | Select a specific order | So that I can see the order's details. | high
| Yes | 26 | Head Operator | Start production of a new order | The management can see the time an order was started | high
Shirel | Yes | 27 | Head Operator | Pause the production of an order | The management can see the time an order was paused | high
|  | 28 | Head Operator | Record the reason of a stoppage | The management can keep a log of the reasons of stoppages in production | high
Nick | Yes | 29 | Head Operator | Continue the production time of an order | The management can keep track of the length of a stoppage | high
| Yes | 30 | Head Operator | Log in what was done to fix an error | The management can see what actions took place to continue production | high
| Yes | 31 | Head Operator | Stop the production of an order (done) | The management can see how long it took for that order to be produced | high
| Yes | 32 | Head Operator | Add notes to an order (production line) | Other workers can be updated with the status of the production line | medium
| Yes | 33 | Head Operator | View all notes attached to a production line (per day and order) | I can view other`s notes and get updated | medium
| Yes | 34 | Head Operator | View the initial checklist of an order | See the conditions of the material collected for production | medium
| Yes | 35 | Head Operator | View current order`s details | I can know what pallets need to be produced | high
Shirel | Yes | 36 | Head Operator | View drawings of pallets in order | I can know what pallets need to be produced | high
| Yes | 37 | Head Operator | View drawings' details of pallets in order | I can have more information over the pallets needed | high
Deji | Yes | 38 | Head Operator | Update location for the drop off of the materials for the truck driver | I can easily access the materials when needed | low
| Yes | 39 | Head Operator (Only) | Create the First Batch Quality Check to an order | Make sure the production of the pallets is matching the requirements and log it | high
| Yes | 40 | Head Operator (Only) | Update the First Batch Quality Check to an order | I can add notes when needed to the checklist | medium
| Yes | 41 | Head Operator (Only) | View the First Batch Quality Check to an order | See what was documented | high
Nick | Yes | 42 | Head Operator | Add the number of pallets completed in the production line | I can keep a record of all the pallets produced per production line per day (divided by type) | medium
| Yes | 43 | Shift Supervisor / Head Operator/Production Line Workers/truck driver | View the hourly check ups for the production Machine I am working on | I can view the status of the production machine | high
| Yes | 44 | Shift Supervisor / Head Operator/Production Line Workers/truck driver | Add a new log to the hourly check up for the production machine I am working on | I can report and update the status of a production machine | high
Same as Head Operator (same requierments) | Yes | 45 | Production line workers | View the main page | I can see the status of the current order and production machine I am working on | medium
| Yes | 46 | Production line workers | Start production of a new order | The management can see the time an order was started | high
| Yes | 47 | Production line workers | Pause the production of an order | The management can see the time an order was paused | high
| Yes | 48 | Production line workers | Record the reason of a stoppage | The management can keep a log of the reasons of stoppages in production | high
| Yes | 49 | Production line workers | Continue the production time of an order | The management can keep track of the length of a stoppage | high
| Yes | 50 | Production line workers | Log in what was done to fix an error | The management can see what actions took place to continue production | high
| Yes | 51 | Production line workers | Stop the production of an order (done) | The management can see how long it took for that order to be produced | high
| Yes | 52 | Production line workers | Add notes to an order (production line) | Other workers can be updated with the status of the production line | high
| Yes | 53 | Production line workers | View all notes attached to a production line (per day and order) | I can view other`s notes and get updated | medium
| Yes | 54 | Production line workers | View list of orders scheduled for the machine I am logged into | I can see the scheduled orders for the day | medium
| Yes | 55 | Production line workers | View the initial checklist of an order | See the conditions of the material collected for production | medium
| Yes | 56 | Production line workers | View order`s details | I can know what pallets need to be produced | high
| Yes | 57 | Production line workers | View drawings of pallets in order | I can know what pallets need to be produced | high
| Yes | 58 | Production line workers | View drawings' details of pallets in order | I can have more information over the pallets needed | high
| Yes | 59 | Production line workers | Update location for the drop off of the materials for the truck driver by the machine | I can easily access the materials when needed | low
| Yes | 60 | Production line workers | Add the number of pallets completed in the production line | I can keep a record of all the pallets produced per production line per day (divided by type) | medium